## Sheet1
AWS Migration Project Plan
Step by Step Migration:
Step No. | Description | Deliverable | Timeline
1 | Assess Current Infrastructure and Application Dependencies | Inventory of current infrastructure and application components | 2 weeks
2 | Design AWS Architecture and Network Topology | AWS architecture diagram and network topology plan | 3 weeks
3 | Provision AWS Resources | Creation of VPC, EC2 instances, RDS, S3 buckets, etc. | 4 weeks
4 | Configure IAM Roles and Policies | IAM roles and policies documentation | 2 weeks
5 | Implement Data Encryption and Security Groups | Encryption setup for data at rest and in transit, implementation of security groups and ACLs | 3 weeks
6 | Migrate Data to AWS | Migration of database, file storage, and other data to AWS | 3 weeks
7 | Test Application Functionality and Performance | Testing of application features and performance in AWS environment | 3 weeks
8 | Implement Monitoring and Logging Solutions | Configuration of CloudWatch and CloudTrail for monitoring and logging | 2 weeks
9 | Conduct Security Audits and Penetration Testing | Security audit reports and penetration testing results | 2 weeks
10 | Deploy Application to Production Environment | Deployment of application to AWS production environment | 1 week
11 | Monitor and Optimize AWS Resources | Ongoing monitoring and optimization of AWS resources for performance and cost efficiency
Assumptions:
The migration team should have experineced AWS professionals with expertise in AWS services.
The AWS environment will be available for testing migration and after deployment eCommerce (Web Application) performance should also be checked.
The AWS resources will be taken into use for the successful running of eCommerce (Web Application).
This migration plan fulfill the requirement of AWS well architected framework for this project.